## Estimation Plan
Date-wise Estimation Plan - Todozee Document Reader (Surya OCR, GPU on AWS)
Start: Mon Jun 29, 2026 ¦ Core effort: 8.5 person-days ¦ Est. core finish: Thu Jul 09, 2026 ¦ Business days only
# | Phase | Task | Est. effort (days) | Planned start | Planned end | Owner | Dependency
1 | 0. Planning | Requirements analysis & instance/region sizing | 0.5 | Jun 29 (Mon) | Jun 29 (Mon) | DevOps | -
2 | 1. Infrastructure | Write Terraform IaC (EC2, EIP, SG, IAM, CW) | 1 | Jun 30 (Tue) | Jun 30 (Tue) | DevOps | Planning
3 |  | Resolve GPU quota & provision (apply) | 0.5 | Jul 01 (Wed) | Jul 01 (Wed) | DevOps | IaC
4 | 2. App bootstrap | CUDA torch + deps + model download + systemd | 0.5 | Jul 01 (Wed) | Jul 01 (Wed) | DevOps | Provision
5 |  | Verify GPU OCR (image + multi-page PDF) | 0.5 | Jul 02 (Thu) | Jul 02 (Thu) | DevOps | Bootstrap
6 | 3. Networking/HTTPS | DNS A-record + Caddy auto-HTTPS (cert) | 0.5 | Jul 02 (Thu) | Jul 02 (Thu) | DevOps | Provision
7 | 4. Monitoring | CloudWatch alarms/agent + Route53 health + SNS | 1 | Jul 03 (Fri) | Jul 03 (Fri) | DevOps | Provision
8 | 5. CI/CD | GitHub workflows + secrets + green verify | 1 | Jul 06 (Mon) | Jul 06 (Mon) | DevOps | App live
9 | 6. Hardening | Remote S3 state + locking | 0.5 | Jul 07 (Tue) | Jul 07 (Tue) | DevOps | CI/CD
10 |  | Pinned app deps + provider lock | 0.5 | Jul 07 (Tue) | Jul 07 (Tue) | DevOps | CI/CD
11 |  | Keyless OIDC roles (plan + apply) | 0.5 | Jul 08 (Wed) | Jul 08 (Wed) | DevOps | CI/CD
12 |  | terraform plan-on-PR + gated apply in CI | 0.5 | Jul 08 (Wed) | Jul 08 (Wed) | DevOps | OIDC
13 |  | Auto + manual rollback (with live test) | 0.5 | Jul 09 (Thu) | Jul 09 (Thu) | DevOps | CI/CD
14 | 7. Documentation | Runbook + inventory + plan docs | 0.5 | Jul 09 (Thu) | Jul 09 (Thu) | DevOps | All
15 | 8. Follow-up | Lock SSH SG to a specific IP | 0.25 | Jul 13, 2026 | Week 2 | User | post-core
16 |  | Configure production reviewer gate | 0.25 | Jul 13, 2026 | Week 2 | User | post-core
17 |  | Restore translation ASG (full size) | 0.25 | TBD (AWS-dependent) | When quota-24 granted | User | post-core
18 |  | ruff + pip-audit CI gate (optional) | 0.5 | Backlog | Backlog | DevOps | post-core
19 |  | Evaluate HA / multi-AZ (ECS) | 2 | Backlog | Backlog/Future | User | post-core
Calendar Gantt (core work)
Task | Jun 29 Mon | Jun 30 Tue | Jul 01 Wed | Jul 02 Thu | Jul 03 Fri | Jul 06 Mon | Jul 07 Tue | Jul 08 Wed | Jul 09 Thu
Requirements analysis & instance/region sizing
Write Terraform IaC (EC2, EIP, SG, IAM, CW)
Resolve GPU quota & provision (apply)
CUDA torch + deps + model download + systemd
Verify GPU OCR (image + multi-page PDF)
DNS A-record + Caddy auto-HTTPS (cert)
CloudWatch alarms/agent + Route53 health + SNS
GitHub workflows + secrets + green verify
Remote S3 state + locking
Pinned app deps + provider lock
Keyless OIDC roles (plan + apply)
terraform plan-on-PR + gated apply in CI
Auto + manual rollback (with live test)
Runbook + inventory + plan docs
Milestones | Kickoff |  |  |  | App live | HTTPS |  | CI/CD | Hardened+Docs