## Plan of Action
# | Phase | Action item | Status | Owner | Priority | Notes
1 | 0. Planning & prerequisites | Clone repo and analyze the Surya OCR FastAPI app | Done | Claude | - | Custom ocr_api.py on port 8040
2 |  | Confirm GPU requirement; choose instance type & region | Done | User+Claude | - | g4dn.xlarge (T4), ap-south-1
3 |  | Verify tooling (AWS CLI, Terraform, credentials) | Done | Claude | - | Account 637560253183
4 | 1. Infrastructure (Terraform) | Write IaC: EC2, EIP, SG, IAM, CloudWatch | Done | Claude | - | main.tf, variables, outputs, user_data
5 |  | Resolve GPU vCPU quota conflict | Done | User+Claude | - | Scaled translation ASG 2->1 (approved)
6 |  | terraform apply - provision instance + EIP | Done | Claude | - | EIP 52.66.27.31
7 | 2. Application bootstrap | Install CUDA torch + deps; download models | Done | user_data | - | torch 2.12.1+cu130, CUDA=True
8 |  | systemd service (uvicorn :8040) | Done | user_data | - | todozee-doc-reader.service
9 |  | Verify GPU OCR on image + multi-page PDF | Done | Claude | - | Correct text, bboxes, ~1.7GB VRAM
10 | 3. Networking & HTTPS | Add DNS A-record (Cloudflare) | Done | User | - | docreader.chatbucket.chat -> EIP
11 |  | Caddy auto-HTTPS / Let's Encrypt cert | Done | Claude | - | Auto-renew; verified over HTTPS
12 | 4. Monitoring & alerting | CloudWatch alarms + agent (mem/disk/GPU) | Done | Claude | - | status-check, CPU>90%
13 |  | Route 53 health check + SNS email | Done | Claude+User | - | Alarm OK; email confirmed
14 | 5. CI/CD | Push terraform + workflows to GitHub | Done | User+Claude | - | main; secrets added by user
15 |  | Deploy workflow (SSH git-pull + restart) | Done | Claude | - | Verified green end-to-end
16 |  | CI gate -> deploy; health check as own step | Done | Claude | - | deploy.yml chained
17 | 6. Hardening (industry standard) | Remote S3 state + S3-native locking | Done | Claude | - | Bucket versioned/encrypted
18 |  | Pinned app dependency lockfile | Done | Claude | - | requirements.lock.txt
19 |  | Commit multi-platform provider lock | Done | Claude | - | .terraform.lock.hcl
20 |  | Keyless OIDC roles (plan + apply) | Done | Claude | - | No long-lived AWS keys
21 |  | terraform plan-on-PR + manual gated apply | Done | Claude | - | Verified via OIDC
22 |  | Auto + manual rollback (live-tested) | Done | Claude | - | Recovered with zero downtime
23 | 7. Documentation | DEPLOYMENT.md runbook | Done | Claude | - | Architecture, ops, teardown
24 |  | AWS services inventory (xlsx) | Done | Claude | - | aws-services.xlsx
25 |  | Plan of Action + Timeline (this file) | Done | Claude | - | PLAN_OF_ACTION.xlsx
26 | 8. Remaining / recommended | Configure 'production' environment required-reviewer | Pending | User | Medium | GitHub UI; needs repo admin
27 |  | Restore translation ASG when GPU quota-24 approved | Pending | AWS+User | Medium | Currently 1 node; case CASE_OPENED
28 |  | Lock SSH (port 22) SG to a specific IP | Recommended | User | Medium | Currently 0.0.0.0/0
29 |  | Add ruff + pip-audit CI gate | Optional | Claude | Low | Deferred - low value for stable wrapper
30 |  | Evaluate HA/multi-AZ (containerize -> ECS) | Future | User | Low | Tier 3; cost+quota dependent

## Timeline
Deployment Timeline - Todozee Document Reader (Surya OCR, GPU)
Phases 0-7 were executed in a single session on 2026-06-29 (Day 0). Open items are projected forward.
Milestone | Phase | Target window | Date | Status
Infra provisioned (EC2 GPU + EIP) | 1 | Day 0 | 2026-06-29 | Done
App live on GPU (OCR verified) | 2 | Day 0 | 2026-06-29 | Done
Public HTTPS live (DNS + cert) | 3 | Day 0 | 2026-06-29 | Done
Monitoring + email alerts active | 4 | Day 0 | 2026-06-29 | Done
CI/CD pipeline green end-to-end | 5 | Day 0 | 2026-06-29 | Done
Hardening done (state/deps/OIDC/rollback) | 6 | Day 0 | 2026-06-29 | Done
Documentation delivered | 7 | Day 0 | 2026-06-29 | Done
Lock SSH SG to specific IP | 8 | Week 1 | by 2026-07-06 | Recommended
Configure production reviewer gate | 8 | Week 1 | by 2026-07-06 | Pending
Restore translation ASG to full size | 8 | When AWS grants quota-24 | TBD | Pending
Optional: ruff + pip-audit gate | 8 | Backlog | - | Optional
Future: HA / multi-AZ (ECS) | 8 | Backlog | - | Future
Schedule (Gantt)
Workstream | Jun 29 (Day 0) | Week 1 (by Jul 6) | Week 2 (by Jul 13) | When quota approved | Backlog / Future
Phases 0-7: Deploy + hardening + docs | Done
Lock SSH SG to specific IP |  | Planned
Configure production reviewer gate |  | Planned
Restore translation ASG |  |  |  | Planned
ruff + pip-audit gate (optional) |  |  |  |  | Later
HA / multi-AZ (future) |  |  |  |  | Later
Legend: | Done | Planned | Later